## Tabelle1
caption | description | category | Priority | edited by | solved | done
Menu structure | Build a general menu structure | Core | very high | my-reality@gmx.de | 2012-03-18 | TRUE
Javadoc | Create comments for javadoc | Doc | very high | my-reality@gmx.de | 2012-03-19 | TRUE
Objectslots | Implement game object slots | Ingame | very high | my-reality@gmx.de | 2012-03-22 | TRUE
Collision | Create tile collision | Ingame | very high | my-reality@gmx.de | 2012-03-22 | TRUE
Configuration | Create a configuration class to load and set settings | Core | high | my-reality@gmx.de | 2012-03-21 | TRUE
Version 0.1 | Milestone | Core |  |  | 2012-03-22 | TRUE
Font | Create Angelic Fonts for the game | Design | very high | my-reality@gmx.de | 2012-03-23 | TRUE
SettingsMenu | Create the Settings Menu | Core | very high | my-reality@gmx.de | 2012-03-23 | TRUE
StateButton | Create a button with different states | GUI | very high | my-reality@gmx.de | 2012-03-24 | TRUE
Captions | Implement menu captions | GUI | very high | my-reality@gmx.de | 2012-03-23 | TRUE
GameSettings | Implement game settings menu | Core | very high | my-reality@gmx.de | 2012-04-01 | TRUE
Comments | Update current code comments | Code | medium | my-reality@gmx.de | 2012-03-28 | TRUE
Version 0.2 | Milestone | GUI |  |  | 2012-03-28 | TRUE
Collision | Fix collision detection bug | WorldMap | very high | my-reality@gmx.de | 2012-04-04 | TRUE
Unit System | Create a general unit class with animation and XML | WorldMap | very high | my-reality@gmx.de | 2012-04-02 | TRUE
Comments | Update comments of the new files | Code | medium | my-reality@gmx.de | 2012-04-05 | TRUE
Map-Loading | Load the map with the game settings | WorldMap | very high | my-reality@gmx.de | 2012-04-02 | TRUE
Daytime | Implement different daytime | WorldMap | very high | my-reality@gmx.de | 2012-04-02 | TRUE
Player colors | Solve color bug on map creation | WorldMap | very high | my-reality@gmx.de | 2012-04-04 | TRUE
Version 0.3 | Milestone | WorldMap |  |  | 2012-04-05 | TRUE
bottom game menu | Create a general menu rid | GUI | very high | my-reality@gmx.de | 2012-04-05 | TRUE
Minimap | Create a left-sided minimap | GUI | high | my-reality@gmx.de | 2012-04-11 | TRUE
Menu buttons | Create menu buttons | GUI | high | my-reality@gmx.de | 2012-04-05 | TRUE
Unit info | Create a unit info system (including unit image on the right) | GUI | high | my-reality@gmx.de | 2012-04-06 | TRUE
Map sound | Implement map background sound (XML | Sound | very high | my-reality@gmx.de | 2012-04-06 | TRUE
Selection | Select units | GUI | high | my-reality@gmx.de | 2012-04-06 | TRUE
Top Menu | Implement top menu with playerinfo | GUI | high | my-reality@gmx.de | 2012-04-11 | TRUE
Animation bars | Animate life and experience bar | GUI | high | my-reality@gmx.de | 2012-04-08 | TRUE
Loading screen | Implement a loading screen | Core | very high | my-reality@gmx.de | 2012-04-08 | TRUE
Smooth Camera Movement | When camera moves to a point, it should moves smoothy | GUI | high | my-reality@gmx.de | 2012-04-08 | TRUE
Debugger | Create a full functional debugger | Debug | high | my-reality@gmx.de | 2012-04-09 | TRUE
Icon Button | Implement an icon button | GUI | high | my-reality@gmx.de | 2012-04-09 | TRUE
Version 0.4 | Milestone | GUI |  |  | 2012-04-11 | TRUE
Worldmap | Create a new map selection system | Core | high | my-reality@gmx.de | 2012-04-11 | TRUE
Updater | Checking for new updates before the intro | Core | high | my-reality@gmx.de | 2012-04-12 | TRUE
Popup Box | Implement an additional popup box for each gui | GUI | high | my-reality@gmx.de | 2012-04-12 | TRUE
FlashBox | Implement an additional flash box | GUI | high | my-reality@gmx.de | 2012-04-12 | TRUE
Daytime | Animate the ambient colors dependend on time | Graphics | high | my-reality@gmx.de | 2012-04-15 | TRUE
Round System | implement a round based system | Gameplay | very high | my-reality@gmx.de | 2012-04-15 | TRUE
Frame timer | Change the timer into a frame based functionality | Core | very high | my-reality@gmx.de | 2012-04-18 | TRUE
Popup and Flash | Make the both components more comfortable | GUI | very high | my-reality@gmx.de | 2012-04-18 | TRUE
Position Bug | Fix unit position and mouse position bug | WorldMap | very high | my-reality@gmx.de | 2012-04-18 | TRUE
Initialization phase | implement an initialization phase with unit selection | Gameplay | very high | my-reality@gmx.de | 2012-04-18 | TRUE
Popup Bug | If element isn't more visible, fade out popup | GUI | very high | my-reality@gmx.de | 2012-04-18 | TRUE
Experience Sounds | Implement sounds when a unit gets experience (with pitch effect) | Sound | very high | my-reality@gmx.de | 2012-04-18 | TRUE
Version 0.5 | Milestone | Gameplay |  |  | 2012-04-18 | TRUE
JavaMail | Implement Java mail | Core | very high | my-reality@gmx.de | 2012-05-10 | TRUE
Bug report screen | Implement a screen in order to report a occurred bug | Debug | very high | my-reality@gmx.de | 2012-04-22 | TRUE
GameUpdater | implement an algorithm to update the game | Core | very high | my-reality@gmx.de | 2012-04-22 | TRUE
Round Tracker | Implement a round tracker and a graph-overview after each game. | GUI | very high | my-reality@gmx.de | 2012-04-30 | TRUE
MovingBug | Solve the moving bug caused by MovementCalculator | Core | very high | my-reality@gmx.de | 2012-04-27 | TRUE
Update Bug | Fix bug that contains the problem that not all data will be updated (FileNotFoundException) | Core | very high | my-reality@gmx.de | 2012-05-13 | TRUE
Multiple Centers | Implement multiple commando centers | Gameplay | very high | my-reality@gmx.de | 2012-04-30 | TRUE
Screenshot Bug | Fix the bug that only one shot can be made | Core | very high | my-reality@gmx.de | 2012-05-01 | TRUE
Gamestate wrapper | Implement a gamestate wrapper | Core | high | my-reality@gmx.de | 2012-04-18 | TRUE
Movement bug | Fix the movement problem with wrong directions | Core | very high | my-reality@gmx.de | 2012-04-19 | TRUE
ContextMenu | Implement a popup context menu | GUI | very high | my-reality@gmx.de | 2012-05-10 | TRUE
PathFinder | Implement a PathFinding system for the tiledmap | WorldMap | very high | my-reality@gmx.de | 2012-04-22 | TRUE
Movement Arrow | Create an arrow that shows the direction path of an unit | Gameplay | high | my-reality@gmx.de | 2012-05-01 | TRUE
Battlesystem | Implement a battle with fancy graphics | Core | very high | my-reality@gmx.de | 2012-06-01 | TRUE
Value Info animation | When a unit gets damage show it and fade it out | GUI | high | my-reality@gmx.de | 2012-06-17 | TRUE
world selector | Fix the bug that the planets are unsynchronized | Bug | very high | my-reality@gmx.de | 2012-06-14 | TRUE
EditText | Fix the bug that the GUI component "EditText" doesn't work correctly. | Bug | very high | my-reality@gmx.de | 2012-06-17 | TRUE
Spawn Radius | Implement a fully integrated spawn radius system | Gameplay | very high | my-reality@gmx.de | 2012-06-12 | TRUE
Version 0.6 | Milestone | Core |  |  | 2012-06-17 | TRUE
Spawn Radius | Make spawn radius more efficiently and make it removable | Gameplay | very high | my-reality@gmx.de | 2012-06-22 | TRUE
GitHub Support | Rewrite Updater and Website for GitHub | Core | very high | my-reality@gmx.de | 2012-06-24 | TRUE
File Scanner | Create a file scanner in order to scan the file structure | Core | very high | my-reality@gmx.de | 2012-06-26 | TRUE
Language | Complete all language keys | Core | very high | my-reality@gmx.de | 2012-06-27 | TRUE
Win logic | Implement logic to win the game | Gameplay | very high | my-reality@gmx.de | 2012-06-28 | TRUE
Popup Menu Bug | Fade Popup out when specific object isn't active | Graphics | very high | my-reality@gmx.de | 2012-06-29 | TRUE
Movement speed | Make units faster and implement game speed | Core | very high | my-reality@gmx.de |  | FALSE
KI System | Implement KI for all difficultiues | Gameplay | very high |  |  | FALSE
LevelMusic | Music and Sounds should be depended on daytime and weather | Core | very high |  |  | FALSE
Smaller fonts and buttons | Implement a new very small font size "FONT_TINY" and change the size of the buttons | GUI | high |  |  | FALSE
Animation | Implement levelup and exp add animation with particles | Graphics | high |  |  | FALSE
Design - Worlds | Create 3 first worldmaps | Design | high |  |  | FALSE
Design - Creatures | Create first 2 units | Design | high |  |  | FALSE
Design - Maps | Create a desert setting tileset and create maps | Design | high |  |  | FALSE
Design - Sounds | Implement sounds for each creature | Design | high |  |  | FALSE
Animations | set up the different animations for each state | Graphics | very high |  |  | FALSE
Click on non-centered unit | Fix unit moving, when click on an unit and it moves instead | Bug | very high |  |  | FALSE
Version 0.7 | Milestone | Gamedesign |  |  |  | FALSE
Save game | save a game | Core | very high |  |  | FALSE
Load game | load a game | Core | very high |  |  | FALSE